## Status Report
Project Name | ASQ QUIZ |  |  | Client |  | ITU / ASQ | Team |  | MEAN Team
Project Summary |  |  |  |  | Key Phases |  | Progress | Status
This WebApp will provide a platform for students/users of ASQ to study in QA methodology. Provides 3 major functionalities Exam Mode, Practice Mode and History. Project is On Track and under the Budgetting Limits. Might have to add few additional resources to make sure project gets delivered on time. |  |  |  |  | Analysis |  | 100% | Complete
[5 empty] | Debuging |  | 100% | Complete
[5 empty] | UI Development |  | 50% | Phase 1 Complete
[5 empty] | Modules Development |  | 60% | On Track
[5 empty] | Modules Integration |  | 30% | Delayed
[5 empty] | QA & Test Cases |  | 60% | On Track
[5 empty] | Questions Population |  | 0% | Future Task
[5 empty] | Product Delivery |  | 0% | Future Task
Tasks Completed |  |  |  | Tasks Delayed |  |  | Tasks Planned
Analysis of the key components. Debugging and Making the Existing App Features Work. Phase 1 of UI Development. Several individual modules essential for the App Upgrade. |  |  |  | Integration is ongoing and delayed as we have trouble integrating some moudules. |  |  | Testing of the modules & application integration. Development of the next set of modules. Begin Phase 2 of UI Development.
Project Budget |  |  |  | Key Project Risks and Issues
Item Description |  | Forecast | Actual | Type | Risks or Issue Description
Development Cost |  | 60000 | 40000 | Risk | Even though work is on track, there could be fear of delays in the product being ready in time.
Infrastructure Cost |  | 30000 | 20000
Buffer & Overhead |  | 12000 | 5000
Startup Discount |  | -2000 | 0 | Issue | Some Integration Issues been reported the project team. We had planned some integration solutions and we will be discussing results on next team meeting. There could be some impact to the schedule.
Total |  | 100000 | 65000