## Plan
Initial Work
1. Collect Requirements
2. Collect Existing Project
3. Stripe the Application and find out functional dependencies
4. Decide on improvements
Development
1. Build new UI plan
2. Debug and make app work
3. Build working form validation
4. Build two factor authentication
5. Build Database Encryption and Decryption Function
6. Build bulk import function to import questions
7. Implement UI Plan
8. Integrated Testing on each function build
Final
1. Load Questions
2. Test everything
3. Tweak the application for improvements

## WBS (Inherited&Updated)
Work Breakdown Structure
PROJECT SYSTEM | [8 empty] | OTHER PROJECT TOOLS
Level 1 WBS | [5 empty] | 0. ASQ CSQE Web App |  |  | Project Name
Level 2 WBS | 1. Front-End |  |  |  |  | 2. Back-End | 3. Database |  | Phase/ Component
Level 3 WBS | 1.1 User Log-in/logout | 1.2 Create User Account | 1.3 Practice Mode" | 1.4 Exam Mode Mode" | 1.5 Front View Template Mode" | 2.1 Log In/Log Out Validation | 3.1 Create Db | 3.2 Upload Questions | Task
| 1.1.1 Req'd fields Validation | 1.2.1 Format Validation (email + fields req) | 1.3.1 ModeSelection | 1.4.1 Mode Selection | 1.5.1 Add Additional Pages | 2.2 Create Account | 3.1.1 Db schema | 3.2.1 Save Results
|  | 1.2.2 Password Validation | 1.3.2 Display Questions | 1.4.2 Display Questions |  | 2.3 Query Db and send results to frontend | 3.1.2 Data Encrypt | 3.2.2 Bulk Import Questions
|  | 1.2.3 Two Factor Authentication | 1.3.3 Grade Questions & Display Results | 1.4.3 Grade Questions & Display Results |  |  | 3.1.3 Data Decrypt
1.4.4 Countdown Timer

## Estimation
Task | Assigned To | Work Load (in days) | Status | Comments
Collect Requirements | Yogesh | 3 days | completed
Collect Existing Project | Yogesh | 2 days | completed
Stripe Application and Find Dependencies | Yogesh | 3 days | completed
Decide on Improvements | Team | 2 days | completed
Debug and Make Application Work | Team | 7 days | completed
Test Application to build Initial Test Cases | Testing team | 3 days | completed
Build New UI plan | Yogesh | 3 days | completed
Build Updated Form Validations | Diaa | 4 days | completed
Integrate Form Validations | Varsha | 1 day | completed
Test New Integration | Avani | 3 days | completed
Update Test Cases | Akanksha | 2 days | completed
Log defects | Avani | 1 day | completed
Build DB Encrypt/Decrypt Function | Varsha | 4 days | completed
Trial Integrate DB Encrypt/Decrypt Function | Varsha | 3 days | completed
Test Integreation | Akanksha | 3 days | completed
Update Test Cases | Avani | 2 days | completed
Log defects | Akanksha | 1 day | completed
Build Two Factor Authentication Function | Diaa | 3 days | completed
Integrate TFA Function | Diaa | 2 days | completed
Test Integreation | Avani | 3 days | completed
Update Test Cases | Akanksha | 2 days | completed
Log defects | Avani | 1 day | completed
Test Integreation | Avani | 3 days | completed
Update Test Cases | Akanksha | 2 days | completed
Log defects | Avani | 1 day | completed
Build Phase 1 UI Design | Yogesh | 3 days | completed
Integrate Phase 1 UI Design | Diaa | 3 days | completed
Test Integreation | Akanksha | 3 days | completed
Update Test Cases | Avani | 2 days | completed
Log defects | Akanksha | 1 day | completed
Build Phase 2 UI Design | Diaa | 3 days | completed
Integrate Phase 2 UI Design | Varsha | 2 days | completed
Test Integreation | Avani | 3 days | completed
Update Test Cases | Akanksha | 2 days | completed
Log defects | Avani | 1 day | completed
Build Final UI Design | Yogesh | 2 days | completed
Integrate Final Design | Diaa | 1 day | completed
Test Integreation | Akanksha | 3 days | completed
Update Test Cases | Avani | 2 days | completed
Log defects | Akanksha | 1 day | completed
Build Question Bank | Varsha | 1 day | completed
Import Question Bank | Varsha | 1 day | completed
Test Quiz Modules | Akanksha | 2 days | completed
Update Test Cases | Avani | 2 days | completed
Populate Other Pages | Diaa | 2 days | completed
Test Contact Page enquiry form and log defects | Akanksha | 1 day | completed
Build Final Test Cases | Avani | 2 days | completed
Fix Final Issues |  | 2 days | completed
Test Integration and log defects | Akanksha | 3 days | completed
Final Tweak to Application | Yogesh | 2 days | completed
Perfrom Full Test | Avani | 2 days | completed
Deliver Application | Team | 2 days | completed